## TPS Report
TPS Report | [5 empty] | Date: | 2015-10-07
Group Names:
Austin Smith
Caleb Viola
Hassan Alshammasy
James Kwapien
Quadratic Project
No. | Description | Time Estimate | Risk Estimate | Who | % Complete | Time Required | Code Review
1 | Floating Point Article | 1 hour | 1 | Caleb | 100% |  | N/A
2 | Read/Overview Article | 4 hours | 3 | All | 25% |  | N/A
3 | Prototype Program | 2 hours | 4 | Caleb | 100% |  | Hassen
4 | Spike: IEEE Standards, INFS, NANS, etc | 2 hours | 3 | James | 0%
5 | C Programming Standard/Compiler Flags
6 | Stories (functional requirements)
7 | Project folder/file structure
8 | Spike: Error | 3 hours | 2 | James | 100% | <3h | Austin
9 | Quadratic Solver sources (texts, etc)
10 | Unit Testing w/ Automation | 4 hours | 4 | James | 25%
11
12
13
Note on D10: Austin Smith: Estimate between 1-10

## Task Board
Task Board
| Open Tasks | Projected Hours | Priority | % Complete | Taken
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Core Requirements
Item | Restraint | Notes